Project Plan

Point Seven Coffee

| Industry Partner | Point Seven Coffee |
| --- | --- |
| Primary Instructor | Anjana Shah |
| Team Member | Andrei Gania |
| Team Member | Denrick Shawn Viera |
| Team Member | Kirk Douglas |
| Team Member | Idrish Kaidawala |
| Team Member | Maaz Akukara |

Document Revision History

| Revision # | Date |
| --- | --- |
| Different database for website and android applications | Feb 01 2026 |

Table of Contents

Page 1-10: Document Revision

Page 3-10:  Executive Summary

Page 3-10:  Project Approvers, Reviews and Distribution List

Page 4-10:  Scope

Page 5-10:  Assumptions

Page 5-10: Dependencies

Page 5-10: Risk and Management

Page 6-10: Communication

Page 6-10: Task Listing (WBS- Work Breakdown Structure)

Page 7-10: Gantt Chart

Page 9-10:  RAM – Responsibility Assignment Matrix

Page 10-10:  Approval

1. Executive Summary

The following describes the project to be executed.

| Objective | To design and develop a centralized digital eco system for Point Seven Coffee, consisting of a customer-facing website and a staff-only Android app. This project will enhance customer engagement, streamline, operations, and strengthen the brand’s digital presence. |
| --- | --- |
| Corporate Goals Addressed | - Expanding the brand’s regional digital presence (Riyadh, Doha, Abu Dhabi, Muscat) - Reducing manual overhead and improving real-time coordination. - Building a scalable digital foundation for future growth |
| Planned Start Date | Nov 2025 |
| Planned End Date | April 2nd 2026 |

2. Project Approvers, Reviews and Distribution List

Approvers, reviewers and distribution list

| Project Role | Name | E-mail | Date |
| --- | --- | --- | --- |
| Primary Instructor | Anjana Shah | ashah@georgebrown |  |
| Project Leader | Idrish Kaidawala | 101498470@georgebrown.ca |  |
| Team Members | Maaz Akukara | 101495272@georgebrown.ca |  |
| Team Members | Kirk Douglas | 101478350@georgebrown.ca |  |
| Team Members | Andrei Gania | 101401017@georgebrown.ca |  |
| UI/UX Designer | Denrick Viera | 101426295@georgebrown.ca |  |
| Industry Partner | Point Seven Coffee |  |  |

Project Scope - The scope of this project includes the full design, development of Point Seven Coffee website, Android app, and backend system. The project encompasses user interface design, database and API development, testing and Documentation.

3. Scope

Define the sum total of all of its products and their requirements or features.

| In Scope | Out of Scope |
| --- | --- |
| Website design and front-end development | Point-of-sale (POS) and payment gateway integration beyond PayPal |
| Staff-only Android application | Physical infrastructure or hardware procurement |
| Database design and API integration | Non-digital operations such as logistics or supply chain management |
| Admin dashboard for content and operations management |  |
| Deployment on hosting servers |  |
| Documentation (technical and user guides) |  |

This project will deliver the following.

| Deliverable | Description |
| --- | --- |
| Customer Website | Fully Responsiveness website featuring menu, locations, events, merchandise store, and contact form. |
| Android App | Internal Staff app with scheduling, inventory management, and communication |
| Admin Dashboard | Backend interface to manage shifts, inventory management, and communication |
| Database and API | Secure architecture is implemented where the app and website operate on separate databases with no real-time synchronization between them. |
| Documentation | Comprehensive user manual and developer guide for maintenance |
| Final Presentation | Live demonstration of project outcomes and technical report submission |

5. Assumptions

This project makes the following assumptions;

- All required brand assets and content (menu, logo, images) will be provided by Point Seven Coffee.

- All team members will maintain communication and meet regularly to ensure progress.

- Required tools (Android Studio, VS Code, GitHub, hosting) are accessible.

- Stakeholders will provide timely feedback during review stages.

6. Dependencies

The following are the internal and external dependencies that will have to be acknowledged and addressed;

- UI/UX designs have been formally approved by Point Seven management, allowing development to proceed.

- Availability of Android development tools and compatible testing devices.

- Stable hosting environment and backend deployment support.

- Ongoing communication between student team and industry partner for alignment.

7. Risk Management

| Potential Risk | Severity (H/M/L) | Likelihood (H/M/L) | Management Strategy |
| --- | --- | --- | --- |
| Client feedback | High | Medium | Set fixed review dates and maintain communication logs.. |
| Data synchronization errors | High | Medium. | Perform frequent integration testing with version control. |
| Team member absence. | Medium | Medium | Assign secondary roles and cross-train members. |
| Scope creep | High | Medium | Lock deliverables early and require instructor approval for changes. |
| Technical issues with hosting or deployment | Medium | Low. | Prepare backup environments and maintain documentation.. |

8. Communication

Reporting

The following reports will be produced;

| Report | Audience | Frequency |
| --- | --- | --- |
| Weekly status updates | Instructor & Partner | Weekly |
| Sprint progress report | Team members | Bi-weekly |
| Final progress summary | All stakeholders | End of project |

Meetings

The following meetings/communication will be established;

| Meeting | Purpose | Attendees | Frequency |
| --- | --- | --- | --- |
| Stand-up meeting | Review weekly goals and challenges. | Team | Weekly |
| Client review. | Feedback and direction | Partner & Team Lead. | Bi-weekly |
| Instructor check-in | Academic feedback and grading updates | Instructor & Team | Monthly |

9. Task Listing (WBS- Work Breakdown Structure)

The following resource proposal template summarizes the resource hours committed to this project, upon final approval of this document.

| Reference | Tasks | Duration | Dependency |
| --- | --- | --- | --- |
| A | Requirement Gathering & Analysis. | 2 weeks |  |
| B | UI/UX Design for Website & App. | 2 weeks | A. |
| C | Backend Development (API & Database) | 3 weeks | B |
| D | Website Frontend Development | 3 weeks | C |
| E | Android App Development | 3 weeks | C |
| F | Testing & Integration | 2 weeks | D, E |
| G | Documentation & Final Report | 1 week | F |

10. Gantt Chart

Create a detailed Gantt Chart from your Task Listing(Use any software tool and paste the image or upload as a separate file that can be opened as pdf/doc/xls) Below is an example:

| Task | Period |  |  |  |  |  |  |  |  |  | Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dates | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE |  |
| A | Requirements Gathering & Analysis |  |  |  |  |  |  |  |  |  | Completed |
| B | UI/UX Design (Website + App) |  |  |  |  |  |  |  |  |  | Completed |
| C | Backend & API Development |  |  |  |  |  |  |  |  |  | In progress |
| D | Website Frontend Development |  |  |  |  |  |  |  |  |  | In progress |
| E | Android App Development |  |  |  |  |  |  |  |  |  | In progress |
| F | Testing & Integration. |  |  |  |  |  |  |  |  |  | In progress |
| G | Documentation & Deployment |  |  |  |  |  |  |  |  |  |  |
| H | Final Presentation & Submission. |  |  |  |  |  |  |  |  |  |  |

11. Milestones

| Major Activity or Milestone | Estimated Milestone Target date | Owner/Reviewer Team Members |
| --- | --- | --- |
| Project Kickoff | Nov 2025 | Team Lead |
| Requirements Approved | Dec 2025 | Partner |
| Design Approval | Jan 2026 | Instructor & Partner. |
| Backend Completion | Feb 2026 | Entire Team |
| Website & App Alpha Release | Mar 2025 | QA Team |
| Final Deployment & Testing | Apr 2025 | Full Team |
| Final Presentation | Apr 2025 | Entire Team |

12. RAM – Responsibility Assignment Matrix

Create a RAM from your Task Listing. A sample is shown below:

| Project Team Responsibilities Project Name: Point Seven Coffee Digital Experience Project Manager: Idrish Kaidawala |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task | Idrish kaidawala | Andre Gania | Maaz Akukara | Kirk Douglas | Denrick Viera |
| Requirements Gathering & Analysis | P | P | P | P | P |
| UI/UX Design (Website + App) | P | P | P | S | S |
| Website Frontend Development | P | S | P | S | S |
| Android App Development | S | P | S | P | P |
| Testing & Integration | P | P | S | P | P |
| Testing & Integration. | P | P | P | P | P |
| Documentation & Deployment | P | S | S | P | S |
| Final Presentation & Submission. | P | P | P | P | P |

13. Approval

The signatures below indicate their approval of the contents of this document.

| Project Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Industry Partner | Point Seven Coffee |  | Feb 8, 2026 |
| Instructor | Anjana Shah |  | Feb 8, 2026 |
| Team Lead | Idrish Kaidawala |  | Feb 8, 2026 |
| Team Members | Maaz Akukara |  | Feb 8, 2026 |
| Team Members | Kirk Douglas |  | Feb 8, 2026 |
| Team Members | Andrei Gania |  | Feb 8, 2026 |
| Team Members | Denrick Shawn Viera |  | Feb 8, 2026 |